## Test Plan
Please click here for Tasty Treat Test Plan full PDF

## TestScenarios
Project Name | Tasty Treat
Reference Document | FRS
Created By | Sarowar Jaman
Creation Date | 2025-01-01
Approval Date | 2025-01-02
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
(TS_001) Registration Functionality | FRS | Validate the "Register Account" functionality | P1 | 19
(TS_002) Signin Functionality | FRS | Validate the "Sign in" functionality | P1 | 19
(TS_003) Signout Functionality | FRS | Validate the "Sign out" functionality | P2 | 2
(TS_004) Forgot Password | FRS | Validate the working of "Forgot Password" functionality | P1 | 10
(TS_005) Multi Device Functionality | FRS | Validate the Multi Device and Cross Browser functionality | P1 | 1
(TS_006) Home Page | FRS | Validate the working of "Home Page" functionality
(TS_008) Ordering Workflow | FRS | Validate the "Ordering Workflow" functionality
(TS_009) Add to Cart | FRS | Validate the "Add to Cart" functionality
(TS_010) Discount Functionality | FRS | Validate the ability to apply a discount coupon during checkout
(TS_011) Free Home Delivery | FRS | Validate the "Free Home delivery" functionality
(TS_012) Check Out | FRS | Validate the "Check Out" process from the cart
(TS_013) Wishlist | FRS | Validate adding foods to the "Wishlist"
(TS_014) Remove Food Item | FRS | Validate removing food items from the cart
(TS_015) Change Food Quantity | FRS | Validate changing the food quantity from the cart
(TS_016) Payment Gateway | FRS | Validate "Payment Gateway" functionality for different payment methods
(TS_020) Delivery Tracking | FRS | Validate the "Delivery Tracking" functionality

## TestCase
Product Name |  | Tasty Treat | TC Start Date | 13-01-2025 | TC Execution Start Date | - - |  |  |  |  | TEST CASE
Module Name |  | Account | TC End Date | 15-02-2025 | TC Execution End Date | - - |  |  |  |  | PASS | 50
Epic |  |  | Test Case Developed By | Sarowar Jaman | Browser (tested) | Yes |  |  |  |  | FAIL | 8
Developer Name (TL) |  |  | Test Case Reviewed By | Ehsanul Alam Sabbir | Performance (tested) | Yes |  |  |  |  | NO RUN | 0
Test Executed by | [10 empty] | BLOCKED | 0
[11 empty] | TOTAL | 58
#SL | Module | Type of Testing | Test Scenarios | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status | Remarks
1 | Account | Browser Compatibility Testing | Account | Checking by running the URL site in different browsers. | Should be run in different browsers. | Found as per expectation. | Browsers-Chrome, Internet Explorer, Mozilla Firefox, Microsoft Edge, Opera Mini. | 1. Go to different browsers. 2. Search 'Startech' 3. Go to the website. |  |  | Passed
2 |  |  | Registration Functionality | Validate by clicking on the Register button for blank input | Registration shouldnot proceed | Found as per expectation. | None | 1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Register" link. |  |  | Passed
3 |  |  |  | Verify all fields related to registration present on the registration field | All required fields are present | Found as per expectation. | None | 1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Register" link. |  |  | Passed
4 |  |  |  | Password field should have validation for minimum of 8 to maximum of 16 characters | The password is accepted | Found as per expectation. | None | 1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click on the Password. |  |  | Passed
5 |  |  |  | Password must contain one special character, at least one upper case character, and have a numerical | The password is accepted | Found as per expectation. | None | 1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click on the Password. |  |  | Passed
6 |  |  |  | Varify password added by the user shouldbe protected,encrypted,and show in an asterisk(...) | Displayed asterisk(...) | Found as per expectation. | None | 1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click on the Password. |  |  | Passed
7 |  |  |  | Verify an Eye icon added to the password and confirm password field | Presence of Eye icon | Not Found | None | "1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3.Click the "Register" link. 3. Click on the Password and Confirm Password button." |  |  | Failed
8 |  |  |  | Verify captcha is added to the form or not | Presence of captcha | Not Found | None | 1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click on the Register Button |  |  | Failed
9 |  |  |  | Verify that the user adds blank spaces and clicks on the register buton | Error Message should be shown | Succesfully Register | None | 1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Register" link |  |  | Failed
10 |  |  |  | Verify that the user can navigate or access the different controls by pressing the 'Tab' key on the keyboard | Should navigate by pressing'Tab' key | Found as per expectation. | None | 1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Register" link |  |  | Passed
11 |  |  |  | Verify users can register successfully by entering valid credentials | Successfully Register | Found as per expectation. | None | 1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Register" link |  |  | Passed
12 |  |  |  | Test by trying to register with an already registered email address | The email is already registered | Found as per expectation. | None | 1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Register" link |  |  | Passed
13 |  |  |  | Verify that the user isnot allowed to register an accout with the same registered email by adding plus for example useractual+1@gmail.com | Should display error message | OTP is sent to Email | None | 1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Register" link |  |  | Failed
14 |  |  |  | Verify the email varification link was sent to the user's email address successfully | Should display a confirmation message | Found as per expectation. | None | 1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Register" link |  |  | Passed
15 |  |  |  | Verify that the user should not be able to access the application until the user verifies its email by clicking on the link sent to the email | Should not be granted access to the website | Found as per expectation. | None | 1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Register" link. 4. The website must have a feature to send an email for verification after user registration. 5. The user should not have a verified email before starting the test |  |  | Passed
16 |  |  |  | Verify the user is informed to check the spam folder if no emall link is found in the inbox. | Should get a email in Spam | Found as per expectation. | None | 1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Register" link. 4. The website must have a feature to send an email for verification after user registration. 5. If do not see the email in inbox, please check spam or junk folder. 5. The user should not have a verified email before starting the test |  |  | Passed
17 |  |  |  | Verify resend link option is present if the user did not receive the link in the email. | Resend varification link | Found as per expectation. | None | 1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Register" link. 4. The website must have a feature to send an email for verification after user registration. 5. If do not see the email in inbox, please check spam or junk folder. 6. Check the Resend link button |  |  | Passed
18 |  |  |  | Verify resend email link becomes disabled if the user continuously clicks on the resend link | Your resend tries have exceeded | Found as per expectation. | None | 1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Register" link. 4. The website must have a feature to send an email for verification after user registration. 5. If do not see the email in inbox, please check spam or junk folder. 6. Check the Resend link button continously |  |  | Passed
19 |  |  |  | Verify that the required fields are not filled in and clicking the register button will result in a validation error | Should display "Required Field in Mandatory" | Found as per expectation. | None | 1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Register" link |  |  | Passed
20 |  |  |  | Verify all spelling mistakes on the Registration page | Should display no spelling error | Found as per expectation. | None | 1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Register" link |  |  | Passed
21 | [10 empty] | Passed
22 | [10 empty] | Passed
23 | [10 empty] | Passed
24 | [10 empty] | Passed
25 | [10 empty] | Passed
26 | [10 empty] | Passed
27 | [10 empty] | Passed
28 |  |  | Signin Funcionality | Verify Signin screen will appear after clicking on Signin button | Signin screen will appear | Found as per expectation |  | 1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign in" link. 4.Navigate to Signin Screen |  |  | Passed
29 |  |  |  | Verify all Signin related elements and fields are present on the Signin screen | Presence of all elements | Found as per expectation. |  | 1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign in" link. 4.Navigate to Signin Screen |  |  | Passed
30 |  |  |  | Verify that the Signin page of the application is responsive and aligns propery on different screen resolutions and devices | Aligns properly and responsive all tested resolutions and devices | Found as per expectation. |  | 1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign in" link. 4.Navigate to Signin Screen |  |  | Passed
31 |  |  |  | Verify Sign in page title | Correct title in Sign in page | Found as per expectation. |  | 1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign in" link. 4.Navigate to Signin Screen |  |  | Passed
32 |  |  |  | Verify the Title shown on the screen is responsive | Title must be Responsive | Found not as per expection |  | 1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign in" link. 4.Navigate to Signin Screen |  |  | Failed
33 |  |  |  | After the user Sign in page is open, the cursor should remain in the E-mail/Phone text box by default | The cursor should place in E-mail/Phone textbox | Found as per expectation. |  | 1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign in" link. 4.Navigate to Signin Screen |  |  | Passed
34 |  |  |  | Verify that there is a checkbox with the label remember password on the Sign in page | Should presence "Remember me" checkbox | Found as per expectation |  | 1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign in" link. 4.Navigate to Signin Screen |  |  | Passed
35 |  |  |  | Verify that the user will be able to Sign in with their account with correct credential | The user should be successfully logged into the website | Found as per expectation |  | 1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign in" link. 4. Enter valid E-mail/Phone. 5. Enter valid password. |  |  | Passed
36 |  |  |  | Verify that the user can access all controls and elements by pressing the "Tab" key from the keyboard | All interactive controls and elements should be reachable | Found as per expectation |  | 1. Go to the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign in" link. 4. Press the Tab key. 5. Check the focus visibility. 6. Continue pressing the Tab key. 7. Skip Non-interactive elements. 8. End of the Focus Cycle |  |  | Passed
37 |  |  |  | Verify that the password entered in encrypted form. | Password entered should be in encrypted form | Found as per expectation |  | 1. Go to the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign in" link. |  |  | Passed
38 |  |  |  | Verify whether an eye icon is added to the password field | The password field should display an eye icon | Found not as per expectation |  | 1. Go to the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign in" link. |  |  | Failed
39 |  |  |  | Add a Captcha on the Sign in form to prevent the Robot attack | A Captcha should be displayed on the Sign in form | Found not as per expectation |  | 1. Go to the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign in" link |  |  | Failed
40 |  |  |  | Verify the error message should display after just entering an email address and leaving the password field blank | Should display a user-friendly error | Found not as per expectation. |  | 1. Go to the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign in" link |  |  | Passed
41 |  |  |  | Verify the error message should display after just entering password and leaving the email field blank | Should display a user-friendly error | Found as per expectation |  | 1. Go to the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign in" link |  |  | Passed
42 |  |  |  | Check Signed-in user shouldnot sign in on closing the browser | The user must remain Signed-in | Found as per expectation |  | 1. Go to the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign in" link. 4. Verify that the user is successfully signed in and redirected to the dashboard or home page. 6. Close the browser completely. 7. Reopen the browser and navigate to the application URL again. |  |  | Passed
43 |  |  |  | Verify the login session timeout duration.So once logged in a user cannot be authenticated for a lifetime |  | Found as per expectation |  |  |  |  | Passed
44 |  |  |  | Verify that there is a limit to the total number of unseccessfull Signin attempts. | Account is temporarily locked | Found as per expectation |  | 1. Go to the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the "Sign in" link. Enter invalid Email and password ans click Sign in. 4. Verify that the Sign in attempt is failed. 5. Repeat this steps 3-5 multiple times.After some unsuccessfull attempts Error message should display. |  |  | Passed
45 |  |  |  | Verify signed-in user copies the URL and pastes it into a new browser window | Should redirect to the Sign Page | Found as per expectation |  | "1. Go to the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the ""Sign in"" link. Enter valid credentials and click "Sign in" button. 4. Verify that the user is successfully signed in and redirected to the dashboard and copy the URL. 5. Open a new browser window (not a tab) or a private/incognito window and paste it." |  |  | Passed
46 |  |  |  | Prevent Sign in page from SQL injection attack | Sign in attempt fail | Found as per expectation |  | "1. Go to the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the ""Sign in"" link. 4. Enter the following malicious input into the email field: Input: admin@example.com' OR '1'='1 5. Enter a random or blank password. Input: randomPassword123 6. Click the "Sign In" button. 7.Observe the behavior." |  |  | Passed
47 |  |  | Forgot Password Functionality | Verify forgot password link | "Forgot Password" link should be visible on the screen | Found as per expectation |  | "1. Go to the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the ""Sign in"" link. 4. Locate the "Forgot Password" link. 5. Click the link and verify the redirection." |  |  | Passed
48 |  |  |  | Verify that clicking the"Forgot Password" link opens the password recovery page | Password reset form should appear | Found as per expectation |  | "1. Go to the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the ""Sign in"" link. 4. Locate the "Forgot Password" link. 5. Click the link and verify the redirection." |  |  | Passed
49 |  |  |  | Verify that the Email field is present on the forgot password page to recover the password | Should display an input field labeled "Email" | Found as per expectation |  | "1. Go to the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the ""Sign in"" link. 4. Locate the "Forgot Password" link. 5. Click the link and verify the redirection." |  |  | Passed
50 |  |  |  | Verify that when the user updates their password,a email is sent their mail box | A mail should send to users mail box | Found not as per expectation |  | "1. Go to the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the ""Sign in"" link. 4. Locate the "Forgot Password" link. 5. Click the link and verify the redirection. 6.Enter the Email then must go a email to their mail box." |  |  | Failed
51 |  |  |  | Verify when the user updates password,they are logged out from all browsers and devices | Should be logged out from all active sessions | Found as per expectation |  | "1. Go to the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the ""Sign in"" link. 4. Locate the "Forgot Password" link. 5. Click the link and verify the redirection. 6. Update the password. 7. Verify Logout from All Devices/Browsers." |  |  | Passed
52 |  |  |  | Verify that the link sent ot the user is expire after a certain time | Shoukd link expired after a predifened time period | Found as per expectation |  | "1. Go to the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the ""Sign in"" link. 4. Locate the "Forgot Password" link. 5. Click the link and verify the redirection. 6. Request the linl. 7. Receive the link. 8. Wait for the link to expire. 9. Test the expired link." |  |  | Passed
53 |  |  |  | Verify sent password link is disabled on clicking multiple times on the link as per specification | The link can only be used once | Found as per expectation |  | "1. Go to the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the ""Sign in"" link. 4. Locate the "Forgot Password" link. 5. Click the link and verify the redirection. 6. Request the linl. 7. Receive the link." |  |  | Passed
54 |  |  |  | Verify the error message is display after entering an unregistered Email address | Should display a Error message | Found as per expectation |  | "1. Go to the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the ""Sign in"" link. 4. Locate the "Forgot Password" link. 5. Click the link and verify the redirection. 6. Enter unregistered Email address." |  |  | Passed
55 |  |  |  | Verify the displayed Error message for unregistered Email is meaningful | The error message should specify that the Email isnot registered | Found as per expectation |  | "1. Go to the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the ""Sign in"" link. 4. Locate the "Forgot Password" link. 5. Click the link and verify the redirection. 6. Enter unregistered Email address." 7. Check the meaningful error." |  |  | Passed
56 |  |  |  | Verify the user signin successfully with the new password not by the old password | Should Signin with new password | Found as per expectation |  | "1. Go to the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the ""Sign in"" link. 4. change password. 5. Sign out. 6. Sign in with new password. 7. Verify old password doesnot work." |  |  | Passed
57 |  |  | Sign Out Functionality | Verify Sign out by selecting Sign out option from Account module | User should sign out from the website | Found as per expectation |  |  |  |  | Passed
58 |  |  |  | Verify Sign out option is not displayed under account module before Sign in | Sign out option shouldnot display before Sign in | Found as per expectation |  | "1. Go to the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the ""Sign in"" link. 4. After successfully sign in Sign out option will be visible." |  |  | Passed
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
Negative test
mmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmm

## Test Summary Report
Test Case Report | [6 empty] | Result :
Project Name | Tasty Treat
Module Name | Account. |  |  |  |  | Total No. | Status
Feature Name | Register Account ,Sign in,Sign out
Test Case Version | 1 |  |  |  |  | 50 | PASS
Written By | Sarowar Jaman |  |  |  |  | 8 | FAIL
Executed By | Sarowar Jaman |  |  |  |  | 0 | Not Executed | New Features:- | Testing Scope:- | Testing Environment :Google Chrome Browser
Reviewed By | Ehsanul Alam Sabbir |  |  |  |  | 0 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 50 | 8 | 0 | 0 | 58
Grand Total | 50 | 8 | 0 | 0 | 58
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Reporting
# SL 01
Issue: Verify an Eye icon added to the Password and Confirm Password field
Reproducing Steps:
"1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3.Click the "Register" link. 3. Click on the Password and Confirm Password button."
Env: Production.
Module: Register
Priority: High
Severity: Critical
Screenshot: https://prnt.sc/9jkv3_dYOZ-a
Expected: Presence of Eye Icon
Responsible QA: Sarowar Jaman
Bug Reporting
# SL 02
Issue: Verify Captcha is added to the form or not
Reproducing Steps: "1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click on the Register Button"
Env: Production
Module: Register
Severity: High
Priority: P1
Screenshot: https://prnt.sc/V1vBeevVh6AP
Expected Result: Captcha should be added in the form.
Responsible QA: Sarowar Jaman
Bug Reporting
# SL 03
Issue: Verify that the user adds blank spaces and clicks on the Register button
Reproducing Steps: "1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the ""Register"" link "
Env: Production
Module: Register
Severity: High
Priority: P1
Screenshot: https://prnt.sc/m9stbK-8fHZW
Expected Result: Error Message should be Shown.
Responsible QA: Sarowar Jaman
Bug Reporting
# SL 04
issue: Verify that the user isnot allowed to register an account with the same registered Email by adding plus for example useractual+123@gmail.com
Reproducing Steps: "1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the ""Register"" link"
Module: Register
Env: Production
Severity: High
Priority: P1
Screenshot: https://prnt.sc/pjZJ0pSreXAk
Expected Result: Should display Error message.
Respomsible QA: Sarowar Jaman
Bug Reporting
# SL 05
issue: Verify the Title shown on the screen is responsive.
Reproducing Steps: "1. Goto the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the ""Sign in"" link. 4.Navigate to Signin Screen"
Env: Production
Module: Sign in
Severity: Low
Priority: P2
Screenshot: https://prnt.sc/h7I-ZWjlTm60
Expected Result: Title should be Responsive.
Responsible QA: Sarowar Jaman
Bug Reporting
# SL 06
Issue: Verify whether an Eye Icon is added to the password field.
Reproducing Steps: "1. Go to the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the ""Sign in"" link."
Env: Production
Module: Sign in
Severity: Medium
Priority:P2
Screenshot: https://prnt.sc/0mfQ3waS2xmW
Expected Result: The Password field should have an Eye icon.
Responsible QA: Sarowar Jaman
Bug Reporting
# SL 07
Issue: Add a Captcha on the Sign in form to prevent the Robot attack.
Reproducing Steps: "1. Go to the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the ""Sign in"" link"
Env: Production
Module: Sign in
Severity: High
Priority: P1
Screenshot: https://prnt.sc/cQEZMklIH4z-
Expected Result: Captcha should be displayed in Sign in form.
Responsible QA: Sarowar Jaman
Bug Reporting
# SL 08
Issue: Verify that when the user updates their password a Email is sent to their Mail box
Reproducing Steps: """1. Go to the URL https://tastytreatbd.com/ 2. Click on the Account button in the right corner. 3. Click the """"Sign in"""" link. 4. Locate the ""Forgot Password"" link. 5. Click the link and verify the redirection. 6.Enter the Email then must go a email to their mail box.""
Env: Production
Module: Forgot Password
Severity: Medium
Priority: P1
Screenshot: https://prnt.sc/4rLX5HLqHRdP
Expected Result: A Email should sent to the Mail Box
Responsible QA: Sarowar Jaman
Bug Reporting
# SL 02
Issue: Password and confirm password should have an eye icon
Reproducing Steps:
1. Goto the URL http://localhost:1337 2. Click on the Sign up button at the right corner. 3. Fill all the files with valid credentials. 4. Click 'Register'.
Env: Production
Module: Sign up

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (50/50)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/50)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (45/50)*100 = 90%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (5/50)*100 = 10%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/50)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A